## Sayfa1
WishList.com Task Dependency |  |  | WishList.com Estimates
Work Page | Task | Dependency | Task |  | Optimistic Hour | Realistic Hour | Pessimistic Hour
Preliminary Work | PW1. DB Design |  | Preliminary Work |  | 55 | 71 | 87
Preliminary Work | PW2. UI Design | PW1 | PW1. DB Design |  | 5 | 7 | 9
Preliminary Work | PW3. Architectureral Design | PW2 | PW2. UI Design |  | 15 | 20 | 25
Preliminary Work | PW4. Technical Documentation | PW3 | PW3. Architectureral Design |  | 23 | 27 | 30
Preliminary Work | PW5. Reserch Analysis | PW4 | PW4. Technical Documentation |  | 5 | 7 | 10
Preliminary Work | PW6. Team Introduction | PW5 | PW5. Reserch Analysis |  | 5 | 7 | 9
Technical Analysis | TA1. Determinig the Necessary Inf. Needs | PW6 | PW6. Team Introduction |  | 2 | 3 | 4
Technical Analysis | TA2. Adequacy Analysis of Resources | PW6 | Technical Analysis Work |  | 11 | 15 | 19
Authentication Tasks | AT1. Sign-In | PW6 | TA1. Determinig the Necessary Inf. Needs |  | 5 | 7 | 9
Authentication Tasks | AT2. Sign Up | PW6 | TA2. Adequacy Analysis of Resources |  | 6 | 8 | 10
Authentication Tasks | AT3. Forget Password | AT1 | Dev Work |  | 236 | 292 | 349
Back-End Developer | BE1. User-Admin Database | PW6 | AT1. Sign-In |  | 10 | 12 | 14
Back-End Developer | BE2. Wish List Database | PW6 | AT2. Sign Up |  | 10 | 13 | 16
Back-End Developer | BE3. Product Database | PW6 | AT3. Forget Password |  | 10 | 12 | 14
Back-End Developer | BE4. Integration with "Amazon API" | PW6 | BE1. User-Admin Database |  | 15 | 20 | 25
Create Wish List Page Module | CW1. Front-End Developer | BE2, BE3 | BE2. Wish List Database |  | 15 | 18 | 21
Create Wish List Page Module | CW2. Back-End Developer for Create URL | CW1 | BE3. Product Database |  | 13 | 15 | 17
Create Wish List Page Module | CW3. Front-End Developer for Create URL | CW2 | BE4. Integration with "Amazon API" |  | 15 | 18 | 20
Other Page Module | OP1. Home Page | PW6 | CW1. Front-End Developer |  | 20 | 24 | 28
Other Page Module | OP2. Reservation Page | BE4 | CW2. Back-End Developer for Create URL |  | 8 | 10 | 12
Other Page Module | OP3. Settings Page | PW6 | CW3. Front-End Developer for Create URL |  | 10 | 12 | 14
Other Page Module | OP4. Update User's Information Page | BE1 | OP1. Home Page |  | 18 | 22 | 26
Admin Module | ADM1. Manage Permissions | PW6 | OP2. Reservation Page |  | 14 | 18 | 22
Admin Module | ADM2. Manage Roles | PW6 | OP3. Settings Page |  | 10 | 12 | 14
Admin Module | ADM3. Manage Role Permissions | ADM1, ADM2 | OP4. Update User's Information Page |  | 6 | 8 | 10
Admin Module | ADM4. Manage Users | PW6 | ADM1. Manage Permissions |  | 5 | 7 | 10
Admin Module | ADM5. Manage Users Roles | ADM2, ADM4 | ADM2. Manage Roles |  | 5 | 7 | 10
Admin Module | ADM6. Manage Requests | PW6 | ADM3. Manage Role Permissions |  | 8 | 10 | 12
Admin Module | ADM7. Manage Block The User | ADM5 | ADM4. Manage Users |  | 8 | 10 | 12
Admin Module | ADM8. Manage Reports | PW6 | ADM5. Manage Users Roles |  | 8 | 10 | 12
QA | QA1. Test Planning | PW6 | ADM6. Manage Requests |  | 8 | 10 | 12
QA | QA2. Functional Test | QA1, AT2 | ADM7. Manage Block The User |  | 10 | 12 | 14
QA | QA3. Regression Test | QA2 | ADM8. Manage Reports |  | 10 | 12 | 14
QA | QA4. Smoke Test | QA3 | DevOps Work |  | 13 | 17 | 22
DevOps | D1. Server Configuration | PW6 | D1. Server Configuration |  | 5 | 7 | 10
DevOps | D2. Staging Deployment | QA2 | D2. Staging Deployment |  | 4 | 5 | 6
DevOps | D3. Prod Deployment | QA3 | D3. Prod Deployment |  | 4 | 5 | 6
Other | O1. PM |  | Total Work |  | 315 | 395 | 477
Other | O2. TL |  | QA1. Test Planning | 0.1 | 31.5 | 39.5 | 47.7
Other | O3. Non-Dev | PW6 | QA2. Functional Test | 0.2 | 63 | 79 | 95.4
Other | O4. Bug Fix | QA2 | QA3. Regression Test | 0.2 | 63 | 79 | 95.4
|  |  | QA4. Smoke Test | 0.01 | 3.15 | 3.95 | 4.77
|  |  | O1. PM | 0.2 | 63 | 79 | 95.4
|  |  | O2. TL | 0.2 | 63 | 79 | 95.4
|  |  | O3. Non-Dev | 0.05 | 15.75 | 19.75 | 23.85
|  |  | O4. Bug Fix | 0.25 | 78.75 | 98.75 | 119.25
|  |  | Grand Total |  | 696.15 | 872.95 | 1054.17